## Dashboard
Change & Decision Dashboard
Audit trail for every update, merge, move, removal, dummy classification, and unresolved item.
Metric | Value | Note
Change records | 20 | All include source, reason, impact, classification, and approval.
Approved decisions | 11 | Eleven user decisions.
Dummy/placeholder changes | 4 | Prototype-only classifications.
Open verification | 2 | Registration/domain and other unresolved facts.
Alignment control | Original files remain unchanged. Every aligned deliverable is a new version dated 2026-08-05.

## Change Log
Change Log
Cross-source changes, reasons, impacts, classification, and approval state.
ID | Origin | Previous Data | Latest Data | Priority Source | Reason | Cross-file Impact | Classification | Approval
CL-001 | Blueprint/source hierarchy | Discovery > Brand > module > audit | Website > latest F2 > F1 > supporting | Website/user brief | Implemented structure must control current documentation | All files | DIPERBARUI | Approved
CL-002 | Legal identity | Legal name pending | PT Karya Usaha Sukses operator; 2015; Tangerang | User confirmation | Confirmed business fact | Discovery, Blueprint, Inventory | DIPERBARUI | Approved
CL-003 | Registration | Pending | Still pending official document | User confirmation | Do not invent | All legal references | MENUNGGU VERIFIKASI | Open
CL-004 | Brand descriptor | Kultivate relationship pending | Galdino & Partner by Kultivate | User confirmation | Relationship approved | Blueprint, Inventory | DIPERBARUI | Approved
CL-005 | Public contact | Website values treated as contact | Project/Kultivate placeholder; public GP contact unavailable | User confirmation | Prevent false attribution | Inventory, Missing, Dummy | PLACEHOLDER INTERNAL | Approved classification
CL-006 | Routes | Localized ID slugs and experience/insights | Implemented profile/services/projects/blog/contact | Website | Current routes take priority | Architecture, Routing | DIPERBARUI | Approved
CL-007 | Navigation | Four items + CTA | Home + Profile + Services + Our Experiences + Blog + CTA | Website | Match desktop/mobile implementation | Architecture, Routing | DIPERBARUI | Approved
CL-008 | Profile Detail | Absent in F2 architecture | Three current noindex prototype routes | Website | Record implemented page type | Grouping, Architecture | DITEMUKAN DI WEBSITE TETAPI BELUM ADA DI DOKUMEN | Approved
CL-009 | Service details | Four final pages | Backlog; not current | Website + user | Preserve plan without claiming implementation | Architecture, Routing | TIDAK DITEMUKAN DI WEBSITE | Backlog
CL-010 | Thank You | Separate page | Merged into approved modal target | User | No separate route needed | Architecture, Routing | DIGABUNGKAN | Approved target
CL-011 | Team | Unconfirmed team information | Three dummy prototype identities | User | High-fidelity only | Inventory, Dummy, Missing | DATA DUMMY | Approved classification
CL-012 | Services | Four categories with planned detail | Four categories retained; 15-item catalog prototype | Website + user | Prevent scope inflation | Blueprint, Inventory | PLACEHOLDER INTERNAL | Approved classification
CL-013 | Articles | Reviewed articles required | Six preview-only articles; exclude from launch | User | No legal/editorial approval | Inventory, Missing, Dummy | TIDAK BOLEH TAYANG | Approved classification
CL-014 | Projects | Real proof required | Three dummy cases/testimonials/logos | Website | Prototype only | Inventory, Dummy | DATA DUMMY | Open before launch
CL-015 | Statistics | 280/120/10 and team 9 proposed | Unverified and launch-restricted | F1 + website | No evidence | Discovery, Inventory, Dummy | TIDAK BOLEH TAYANG | Open
CL-016 | Domain | Example legal domain | Target galdinopartner.co.id, not purchased | User | Preserve target without false current claim | Inventory, Missing, Dummy | MENUNGGU VERIFIKASI | Approved target
CL-017 | Inquiry integration | Resend + manual Google Sheets/internal | Resend only | User | Match approved initial flow | Discovery, Routing | DIPERBARUI | Approved
CL-018 | Privacy/Terms | Planned final pages | Backlog/launch blockers; no invented copy | Website + user | Current site has no routes | Architecture, Missing | TIDAK DITEMUKAN DI WEBSITE | Backlog
CL-019 | Brand paper color | #F7F7F5 in Blueprint | #F4F3F1 | Website + Brand Guidelines | Resolve internal conflict | Blueprint, workbooks | DIPERBARUI | Approved derived
CL-020 | Source documents | Original files | Retained unchanged; aligned copies created | User request | Preserve audit trail | All deliverables | DIPERTAHANKAN | Complete

## Decision Log
Decision Log
Explicit decisions supplied by the user on 5 August 2026.
ID | Topic | Decision | Status | Approved By | Date | Impact
D-01 | Current website vs backlog | Website actual is CURRENT; unimplemented F2 pages remain backlog. | Approved | User | 2026-08-05 | Architecture, grouping, routing
D-02 | Contact ownership | Current phone/email are project/Kultivate contacts. | Approved | User | 2026-08-05 | Inventory, contact governance, dummy register
D-03 | Legal identity | Galdino & Partner is operated by PT Karya Usaha Sukses; PT established 2015; domiciled in Kota Tangerang, Banten, Indonesia; registration pending. | Approved | User | 2026-08-05 | Discovery, Blueprint, Profile/legal data
D-04 | Team | Kelvin/Maria/Michael are dummy high-fidelity prototype profiles. | Approved | User | 2026-08-05 | Profile, noindex, dummy register
D-05 | Service catalog | Fifteen items are prototype content under four top-level categories. | Approved | User | 2026-08-05 | Home, Services, inventory
D-06 | Articles | Six articles are preview-only and must not be part of launch without review. | Approved | User | 2026-08-05 | Blog, article governance
D-07 | Domain | galdinopartner.co.id is target domain and is not purchased. | Approved | User | 2026-08-05 | Metadata, SEO, blockers
D-08 | Thank You UX | Use a post-submit modal/pop-up; no separate Thank You page. | Approved target | User | 2026-08-05 | Contact flow, routing
D-09 | Privacy/Terms | No approved policies yet; document website current state without inventing copy. | Approved | User | 2026-08-05 | Backlog and launch blockers
D-10 | Brand relationship | Galdino & Partner by Kultivate may be published. | Approved | User | 2026-08-05 | Brand descriptor/footer/Profile
D-11 | Inquiry integration | Use Resend only for initial version; no Google Sheets/CRM. | Approved | User | 2026-08-05 | Discovery, contact flow

## Cross-file Impact
Cross-file Impact
Traceability from approved decision to every affected deliverable.
Topic | Affected Files | Required Change | Decision ID | Status
Legal identity | Discovery; Blueprint; Inventory; Missing; Master | Update operator/year/city; keep registration pending | D-03 | Complete
Contact classification | Inventory; Missing; Dummy; Master | Mark current values as project/Kultivate placeholder | D-02 | Complete
Current/backlog architecture | Grouping; Architecture; Routing; Master | Separate implemented page types from backlog | D-01 | Complete
Team governance | Inventory; Missing; Dummy; Master | Classify three profiles as dummy/noindex | D-04 | Complete
Service governance | Blueprint; Inventory; Architecture; Dummy | Retain four categories; mark 15 items prototype | D-05 | Complete
Article governance | Inventory; Missing; Dummy; Master | Preview-only; launch exclusion | D-06 | Complete
Domain | Inventory; Missing; Dummy; Master | Target approved, current value remains placeholder | D-07 | Complete
Thank You | Blueprint; Architecture; Routing; Master | Remove separate page; record modal target | D-08 | Complete
Policies | Architecture; Missing; Dummy; Master | Retain backlog and blocker, no invented copy | D-09 | Complete
Brand descriptor | Discovery; Blueprint; Inventory; Master | Use Galdino & Partner by Kultivate | D-10 | Complete
Inquiry delivery | Discovery; Routing; Inventory; Master | Resend only; move Sheets/CRM to backlog | D-11 | Complete

## Source Notes
Source Notes
Source hierarchy and traceability for the change log and decision log.
Source | Priority | Function | Location
Website/codebase aktual | Primary | Implemented route, page structure, navigation, CTA, user flow, feature, and technical behavior. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\website
Dokumen Fase 2 terbaru | Secondary | Architecture and decisions; unimplemented elements are retained as backlog. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\plan\FASE 2
Dokumen Fase 1 | Tertiary | Discovery, business facts, brand foundation, user needs, and project context. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\plan\FASE 1
Brand Guidelines dan audit pendukung | Supporting | Reference only; cannot create claims or expand approved scope. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\brand
Keputusan pengguna 5 Agustus 2026 | Approval | Eleven explicit decisions controlling current/backlog, legal identity, prototype content, domain, inquiry, and governance. | Current Codex task