## Dashboard
Dummy & Placeholder Dashboard
High-fidelity prototype governance and launch release gates.
Metric | Value | Note
Register items | 22 | All identified dummy/placeholder risks.
Data dummy | 5 | Fictitious prototype facts/personas/proof.
Internal placeholders | 10 | Temporary staging values.
Launch restricted | 4 | Review, replace, implement, or remove.
Alignment control | Prototype visibility is allowed only for staging/high-fidelity review. Dummy data must not enter metadata or structured data.

## Dummy Placeholder Register
Dummy & Placeholder Register
Prototype data may remain on staging only under explicit classification and release gates.
ID | Location | Data | Current Value | Classification | Reason | Required Action | Release Gate | Owner | Priority
DP-001 | Global/site data | Legal name in code | [PLACEHOLDER LEGAL NAME] | PLACEHOLDER INTERNAL | User-confirmed operator is PT Karya Usaha Sukses | Update code only under separate approval | Before launch | Website team | P1
DP-002 | Global/site data | Address | [PLACEHOLDER ADDRESS] | PLACEHOLDER INTERNAL | Only Kota Tangerang, Banten is confirmed | Add approved full address or use safe city-level wording | Before launch | Company | P1
DP-003 | Global/site data | Registration number | [PLACEHOLDER REGISTRATION] | MENUNGGU VERIFIKASI | Official number unavailable | Verify official document | Before launch | Company | P1
DP-004 | Metadata | Domain/canonical | https://example-legal-domain.com | PLACEHOLDER INTERNAL | Target galdinopartner.co.id not purchased | Acquire domain and replace | Before launch | Project owner | P1
DP-005 | Header/footer/contact | Phone/WhatsApp | +62 821-2592-4637 | PLACEHOLDER INTERNAL | Project/Kultivate contact | Replace with approved GP public contact | Before launch | Company | P1
DP-006 | Header/footer/contact | Email | kultivatedigitalid@gmail.com | PLACEHOLDER INTERNAL | Project/Kultivate contact | Replace with approved GP public email | Before launch | Company | P1
DP-007 | Home | Client register | ARUNA/NUSA/PRIMA/VERTEX/LINTAS/KARYA | DATA DUMMY | Prototype logos/names | Remove or replace with consented clients | Before launch | Content | P1
DP-008 | Home | Statistics | [DATA] / Menunggu verifikasi | DATA DUMMY | No supporting evidence | Remove or verify | Before launch | Company | P1
DP-009 | Home | 15 service catalog items | Prototype catalog | PLACEHOLDER INTERNAL | Approved only as prototype under four categories | Approve each item or remove | Before launch | Company/legal | P1
DP-010 | Home | Prices | [PLACEHOLDER HARGA] | PLACEHOLDER INTERNAL | No approved pricing | Remove or approve | Before launch | Commercial | P1
DP-011 | Home | Company video | Placeholder media | PLACEHOLDER INTERNAL | No approved asset | Replace or remove section | Before launch | Content | P2
DP-012 | Projects/Home | Experience cards | Three placeholder cases | DATA DUMMY | No evidence/consent | Replace or remove | Before launch | Company/content | P1
DP-013 | Projects | Testimonials/outcomes | Placeholder text | DATA DUMMY | No evidence/consent | Replace or remove | Before launch | Company/content | P1
DP-014 | Profile | Team identities | Kelvin/Maria/Michael | DATA DUMMY | High-fidelity prototype only | Replace or remove; keep noindex until then | Before launch | Company/content | P1
DP-015 | Profile | Team images | Concept/generative imagery | PLACEHOLDER INTERNAL | Not official photography | Replace or remove | Before launch | Content | P1
DP-016 | Profile | Team credentials/contact | Placeholder fields | PLACEHOLDER INTERNAL | No approved evidence | Verify or remove | Before launch | Company | P1
DP-017 | Blog | Six articles | draft:false preview content | TIDAK BOLEH TAYANG | Preview-only by user decision | Legal/editorial review or exclude | At launch | Legal/editorial | P1
DP-018 | Blog | Reviewer/current-law data | Missing | MENUNGGU VERIFIKASI | No reviewer/source/review date | Add governance metadata | Before launch | Legal/editorial | P1
DP-019 | Legal | Privacy Policy | No route/copy | TIDAK DITEMUKAN DI WEBSITE | User approved no invented copy | Draft/review/implement later | Before launch | Legal | P1
DP-020 | Legal | Terms & Disclaimer | No route/copy | TIDAK DITEMUKAN DI WEBSITE | User approved no invented copy | Draft/review/implement later | Before launch | Legal | P1
DP-021 | Structured data | Organization contact/domain | Project contacts/example domain | TIDAK BOLEH TAYANG | Structured data cannot contain provisional facts | Replace verified values or suppress | Before launch | Website/SEO | P1
DP-022 | Technical | robots indexing | Allow all except /api | DIPERBARUI | Prototype pages could be crawled | Protect staging and review production rules | Before public deployment | Website/SEO | P1

## Production Blockers
Production Blockers
Items that must be resolved, suppressed, or removed before launch/public deployment.
ID | Item | Classification | Required Action | Owner | Priority
DP-001 | Legal name in code | PLACEHOLDER INTERNAL | Update code only under separate approval | Website team | P1
DP-002 | Address | PLACEHOLDER INTERNAL | Add approved full address or use safe city-level wording | Company | P1
DP-003 | Registration number | MENUNGGU VERIFIKASI | Verify official document | Company | P1
DP-004 | Domain/canonical | PLACEHOLDER INTERNAL | Acquire domain and replace | Project owner | P1
DP-005 | Phone/WhatsApp | PLACEHOLDER INTERNAL | Replace with approved GP public contact | Company | P1
DP-006 | Email | PLACEHOLDER INTERNAL | Replace with approved GP public email | Company | P1
DP-007 | Client register | DATA DUMMY | Remove or replace with consented clients | Content | P1
DP-008 | Statistics | DATA DUMMY | Remove or verify | Company | P1
DP-009 | 15 service catalog items | PLACEHOLDER INTERNAL | Approve each item or remove | Company/legal | P1
DP-010 | Prices | PLACEHOLDER INTERNAL | Remove or approve | Commercial | P1
DP-011 | Company video | PLACEHOLDER INTERNAL | Replace or remove section | Content | P2
DP-012 | Experience cards | DATA DUMMY | Replace or remove | Company/content | P1
DP-013 | Testimonials/outcomes | DATA DUMMY | Replace or remove | Company/content | P1
DP-014 | Team identities | DATA DUMMY | Replace or remove; keep noindex until then | Company/content | P1
DP-015 | Team images | PLACEHOLDER INTERNAL | Replace or remove | Content | P1
DP-016 | Team credentials/contact | PLACEHOLDER INTERNAL | Verify or remove | Company | P1
DP-017 | Six articles | TIDAK BOLEH TAYANG | Legal/editorial review or exclude | Legal/editorial | P1
DP-018 | Reviewer/current-law data | MENUNGGU VERIFIKASI | Add governance metadata | Legal/editorial | P1
DP-019 | Privacy Policy | TIDAK DITEMUKAN DI WEBSITE | Draft/review/implement later | Legal | P1
DP-020 | Terms & Disclaimer | TIDAK DITEMUKAN DI WEBSITE | Draft/review/implement later | Legal | P1
DP-021 | Organization contact/domain | TIDAK BOLEH TAYANG | Replace verified values or suppress | Website/SEO | P1
DP-022 | robots indexing | DIPERBARUI | Protect staging and review production rules | Website/SEO | P1

## Source Notes
Source Notes
Source hierarchy and traceability for the dummy and placeholder register.
Source | Priority | Function | Location
Website/codebase aktual | Primary | Implemented route, page structure, navigation, CTA, user flow, feature, and technical behavior. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\website
Dokumen Fase 2 terbaru | Secondary | Architecture and decisions; unimplemented elements are retained as backlog. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\plan\FASE 2
Dokumen Fase 1 | Tertiary | Discovery, business facts, brand foundation, user needs, and project context. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\plan\FASE 1
Brand Guidelines dan audit pendukung | Supporting | Reference only; cannot create claims or expand approved scope. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\brand
Keputusan pengguna 5 Agustus 2026 | Approval | Eleven explicit decisions controlling current/backlog, legal identity, prototype content, domain, inquiry, and governance. | Current Codex task