## Dashboard
Architecture Dashboard - Aligned
Current implementation plus retained backlog.
Metric | Value | Note
Current page types | 0 | Includes prototype and preview page types.
Backlog page groups | 0 | Four service details, FAQ, Privacy, Terms.
Merged functions | 2 | Thank You and Process.
Website-found page types | 1 | Profile Detail.
Alignment control | Current routes use profile, services, projects, blog, and contact for both locales. Old localized slugs remain historical only.

## Act 4 Merge Evaluation
Aktivitas 4 - Merge Evaluation Aligned
Every former page decision is retained with current/backlog status and reason.
ID | Halaman Awal | Kondisi | Masalah | Keputusan | Digabung dengan | Nama Akhir | Alasan | Dampak Informasi | Dasar | Status
A-01 | Home | Implemented | None | DIPERTAHANKAN | - | Home | Current orientation page | None | Website | APPROVED
A-02 | Profil | Implemented with English slug | Fase 2 name/URL differs | DIPERBARUI | - | Profile | Follow /[lang]/profile/ | Route/name updated | Website | APPROVED
A-03 | Team Detail | Implemented but absent in Fase 2 | Prototype personas | DITEMUKAN DI WEBSITE TETAPI BELUM ADA DI DOKUMEN | Profile | Profile Detail | Record current prototype | Added as current noindex | Website | APPROVED
A-04 | Layanan | Implemented as hub | No detail pages/dropdown | DIPERBARUI | - | Services | Four categories current | Detail pages moved to backlog | Website + user | APPROVED
A-05 | Pengalaman | Implemented as Projects route | Label/URL differs | DIPERBARUI | - | Our Experiences | Follow /projects/ | Dummy proof retained for prototype | Website | APPROVED
A-06 | Insight | Implemented as Blog route | Label/URL differs | DIPERBARUI | - | Blog | Follow /blog/ | Preview-only governance | Website + user | APPROVED
A-07 | Thank You | No route | User approved modal | DIGABUNGKAN | Contact | Thank You modal | Avoid unnecessary page | Separate page removed | User decision | APPROVED
A-08 | Proses Kerja | Sections on Home | No standalone page | DIGABUNGKAN | Home/Services | Process sections | Matches implementation | No isolated page | Website | APPROVED
A-09 | FAQ | Not implemented | Still useful future function | TIDAK DITEMUKAN DI WEBSITE | - | FAQ | Retain as backlog | No current route | Fase 2 | BACKLOG
A-10 | Privacy | Not implemented | Policy unavailable | TIDAK DITEMUKAN DI WEBSITE | - | Privacy Policy | Retain as launch blocker | No current route | Fase 2 | BACKLOG
A-11 | Terms | Not implemented | Policy unavailable | TIDAK DITEMUKAN DI WEBSITE | - | Terms & Disclaimer | Retain as launch blocker | No current route | Fase 2 | BACKLOG

## Final Page List
Final Page List - Current and Backlog
Eight current page types and seven retained backlog page groups.
ID | Halaman | Jenis/Lifecycle | Parent | Prioritas | Keputusan
F-01 | Home | CURRENT | - | P1 | DIPERTAHANKAN
F-02 | Profile | CURRENT | - | P1 | DIPERBARUI
F-03 | Profile Detail | CURRENT PROTOTYPE | Profile | P2 | DITEMUKAN DI WEBSITE TETAPI BELUM ADA DI DOKUMEN
F-04 | Services | CURRENT | - | P1 | DIPERTAHANKAN
F-05 | Our Experiences | CURRENT PROTOTYPE | - | P1 | DIPERBARUI
F-06 | Blog | CURRENT PREVIEW | - | P1 | DIPERBARUI
F-07 | Article Detail | CURRENT PREVIEW | Blog | P2 | DIPERTAHANKAN
F-08 | Contact | CURRENT | - | P1 | DIPERBARUI
B-01 | Service Detail - Pendirian | BACKLOG | Services | P2 | TIDAK DITEMUKAN DI WEBSITE
B-02 | Service Detail - Risiko | BACKLOG | Services | P2 | TIDAK DITEMUKAN DI WEBSITE
B-03 | Service Detail - Kepatuhan | BACKLOG | Services | P2 | TIDAK DITEMUKAN DI WEBSITE
B-04 | Service Detail - Proyek | BACKLOG | Services | P2 | TIDAK DITEMUKAN DI WEBSITE
B-05 | FAQ | BACKLOG | - | P2 | TIDAK DITEMUKAN DI WEBSITE
B-06 | Privacy Policy | BACKLOG / LAUNCH BLOCKER | - | P1 | TIDAK DITEMUKAN DI WEBSITE
B-07 | Terms & Disclaimer | BACKLOG / LAUNCH BLOCKER | - | P1 | TIDAK DITEMUKAN DI WEBSITE

## Act 5 Page Jobs
Aktivitas 5 - Page Jobs Aligned
One job per current or backlog page.
ID | Halaman | Pekerjaan Utama | Hasil Pengguna | Informasi Pendukung | Pekerjaan Sekunder | Keputusan | Dasar | Catatan
F-01 | Home | Explain relevance and route to consultation or services | User identifies a next action | Brand, four categories, process, prototype proof, latest preview articles | Explore Profile/Projects/Blog | DIPERTAHANKAN | Website/codebase | Primary CTA is consultation
F-02 | Profile | Explain brand, operator, approach, and prototype team | User understands who operates the brand | PT Karya Usaha Sukses, 2015, Tangerang, by Kultivate | Explore team anchor | DIPERBARUI | Website + user decision | Registration/public contact pending
F-03 | Profile Detail | Demonstrate high-fidelity profile pattern | User previews profile structure | Dummy role, expertise, placeholder credential | Return to Profile | DATA DUMMY | Website + user decision | Noindex; remove/replace at launch
F-04 | Services | Orient users to four approved service categories | User selects a relevant category | Four categories, generic scope | Start consultation | DIPERTAHANKAN | Website + user decision | No detail pages
F-05 | Our Experiences | Demonstrate experience/case-study pattern | User sees intended proof structure | Three dummy cases/testimonials | Start consultation | DATA DUMMY | Website | Not factual proof
F-06 | Blog | List preview knowledge content | User finds a topic | Six bilingual preview articles | Open article | TIDAK BOLEH TAYANG | Website + user decision | Exclude from launch until reviewed
F-07 | Article Detail | Explain one regulatory topic in preview | User reads and continues | Article, translation, related posts | Return/read related | TIDAK BOLEH TAYANG | Website + user decision | No reviewer/current-law record
F-08 | Contact | Capture enough context for follow-up | User submits inquiry | Form, consent, validation, Resend | Show approved modal Thank You | DIPERBARUI | Website + user decision | Modal target not implemented
B-01 | Service Detail - Pendirian | Explain detailed scope | User understands scope and exclusions | Deliverables, checklist, timeline | Contact | TIDAK DITEMUKAN DI WEBSITE | Fase 2 | Backlog
B-02 | Service Detail - Risiko | Explain detailed scope | User understands scope and exclusions | Deliverables, checklist, timeline | Contact | TIDAK DITEMUKAN DI WEBSITE | Fase 2 | Backlog
B-03 | Service Detail - Kepatuhan | Explain detailed scope | User understands scope and exclusions | Deliverables, checklist, timeline | Contact | TIDAK DITEMUKAN DI WEBSITE | Fase 2 | Backlog
B-04 | Service Detail - Proyek | Explain detailed scope | User understands scope and exclusions | Deliverables, checklist, timeline | Contact | TIDAK DITEMUKAN DI WEBSITE | Fase 2 | Backlog
B-05 | FAQ | Resolve reviewed common questions | User decides whether to contact | Approved answers | Contact/Services | TIDAK DITEMUKAN DI WEBSITE | Fase 2 | Backlog
B-06 | Privacy Policy | Explain data processing | User understands consent and rights | Approved policy | Contact | TIDAK DITEMUKAN DI WEBSITE | Fase 2 | Launch blocker
B-07 | Terms & Disclaimer | Explain usage boundaries | User understands website limitations | Approved terms | Home/Contact | TIDAK DITEMUKAN DI WEBSITE | Fase 2 | Launch blocker

## Act 6 Page Questions
Aktivitas 6 - Page Questions Aligned
Questions reflect current implementation and approved backlog.
ID | Halaman | Pertanyaan Utama | Pertanyaan Pendukung | Informasi Menjawab | Tersedia? | Kekurangan | Dasar | Status
F-01 | Home | Apakah halaman Home membantu saya mengambil next step yang tepat? | Explain relevance and route to consultation or services | Brand, four categories, process, prototype proof, latest preview articles | TERSEDIA UNTUK STRUKTUR | Primary CTA is consultation | Website/codebase | DIPERTAHANKAN
F-02 | Profile | Apakah halaman Profile membantu saya mengambil next step yang tepat? | Explain brand, operator, approach, and prototype team | PT Karya Usaha Sukses, 2015, Tangerang, by Kultivate | TERSEDIA UNTUK STRUKTUR | Registration/public contact pending | Website + user decision | DIPERBARUI
F-03 | Profile Detail | Apakah halaman Profile Detail membantu saya mengambil next step yang tepat? | Demonstrate high-fidelity profile pattern | Dummy role, expertise, placeholder credential | TERSEDIA UNTUK STRUKTUR | Noindex; remove/replace at launch | Website + user decision | DATA DUMMY
F-04 | Services | Apakah halaman Services membantu saya mengambil next step yang tepat? | Orient users to four approved service categories | Four categories, generic scope | TERSEDIA UNTUK STRUKTUR | No detail pages | Website + user decision | DIPERTAHANKAN
F-05 | Our Experiences | Apakah halaman Our Experiences membantu saya mengambil next step yang tepat? | Demonstrate experience/case-study pattern | Three dummy cases/testimonials | TERSEDIA UNTUK STRUKTUR | Not factual proof | Website | DATA DUMMY
F-06 | Blog | Apakah halaman Blog membantu saya mengambil next step yang tepat? | List preview knowledge content | Six bilingual preview articles | TERSEDIA UNTUK STRUKTUR | Exclude from launch until reviewed | Website + user decision | TIDAK BOLEH TAYANG
F-07 | Article Detail | Apakah halaman Article Detail membantu saya mengambil next step yang tepat? | Explain one regulatory topic in preview | Article, translation, related posts | TERSEDIA UNTUK STRUKTUR | No reviewer/current-law record | Website + user decision | TIDAK BOLEH TAYANG
F-08 | Contact | Apakah halaman Contact membantu saya mengambil next step yang tepat? | Capture enough context for follow-up | Form, consent, validation, Resend | TERSEDIA UNTUK STRUKTUR | Modal target not implemented | Website + user decision | DIPERBARUI
B-01 | Service Detail - Pendirian | Apakah halaman Service Detail - Pendirian membantu saya mengambil next step yang tepat? | Explain detailed scope | Deliverables, checklist, timeline | BELUM TERSEDIA | Backlog | Fase 2 | TIDAK DITEMUKAN DI WEBSITE
B-02 | Service Detail - Risiko | Apakah halaman Service Detail - Risiko membantu saya mengambil next step yang tepat? | Explain detailed scope | Deliverables, checklist, timeline | BELUM TERSEDIA | Backlog | Fase 2 | TIDAK DITEMUKAN DI WEBSITE
B-03 | Service Detail - Kepatuhan | Apakah halaman Service Detail - Kepatuhan membantu saya mengambil next step yang tepat? | Explain detailed scope | Deliverables, checklist, timeline | BELUM TERSEDIA | Backlog | Fase 2 | TIDAK DITEMUKAN DI WEBSITE
B-04 | Service Detail - Proyek | Apakah halaman Service Detail - Proyek membantu saya mengambil next step yang tepat? | Explain detailed scope | Deliverables, checklist, timeline | BELUM TERSEDIA | Backlog | Fase 2 | TIDAK DITEMUKAN DI WEBSITE
B-05 | FAQ | Apakah halaman FAQ membantu saya mengambil next step yang tepat? | Resolve reviewed common questions | Approved answers | BELUM TERSEDIA | Backlog | Fase 2 | TIDAK DITEMUKAN DI WEBSITE
B-06 | Privacy Policy | Apakah halaman Privacy Policy membantu saya mengambil next step yang tepat? | Explain data processing | Approved policy | BELUM TERSEDIA | Launch blocker | Fase 2 | TIDAK DITEMUKAN DI WEBSITE
B-07 | Terms & Disclaimer | Apakah halaman Terms & Disclaimer membantu saya mengambil next step yang tepat? | Explain usage boundaries | Approved terms | BELUM TERSEDIA | Launch blocker | Fase 2 | TIDAK DITEMUKAN DI WEBSITE

## Job Question Alignment
Job and Question Alignment
Audit of page job, visitor question, decision, and remaining dependency.
ID | Halaman | Pekerjaan Utama | Pertanyaan Utama | Keputusan | Catatan
F-01 | Home | Explain relevance and route to consultation or services | Apakah halaman Home membantu saya mengambil next step yang tepat? | DIPERTAHANKAN | Primary CTA is consultation
F-02 | Profile | Explain brand, operator, approach, and prototype team | Apakah halaman Profile membantu saya mengambil next step yang tepat? | DIPERBARUI | Registration/public contact pending
F-03 | Profile Detail | Demonstrate high-fidelity profile pattern | Apakah halaman Profile Detail membantu saya mengambil next step yang tepat? | DATA DUMMY | Noindex; remove/replace at launch
F-04 | Services | Orient users to four approved service categories | Apakah halaman Services membantu saya mengambil next step yang tepat? | DIPERTAHANKAN | No detail pages
F-05 | Our Experiences | Demonstrate experience/case-study pattern | Apakah halaman Our Experiences membantu saya mengambil next step yang tepat? | DATA DUMMY | Not factual proof
F-06 | Blog | List preview knowledge content | Apakah halaman Blog membantu saya mengambil next step yang tepat? | TIDAK BOLEH TAYANG | Exclude from launch until reviewed
F-07 | Article Detail | Explain one regulatory topic in preview | Apakah halaman Article Detail membantu saya mengambil next step yang tepat? | TIDAK BOLEH TAYANG | No reviewer/current-law record
F-08 | Contact | Capture enough context for follow-up | Apakah halaman Contact membantu saya mengambil next step yang tepat? | DIPERBARUI | Modal target not implemented
B-01 | Service Detail - Pendirian | Explain detailed scope | Apakah halaman Service Detail - Pendirian membantu saya mengambil next step yang tepat? | TIDAK DITEMUKAN DI WEBSITE | Backlog
B-02 | Service Detail - Risiko | Explain detailed scope | Apakah halaman Service Detail - Risiko membantu saya mengambil next step yang tepat? | TIDAK DITEMUKAN DI WEBSITE | Backlog
B-03 | Service Detail - Kepatuhan | Explain detailed scope | Apakah halaman Service Detail - Kepatuhan membantu saya mengambil next step yang tepat? | TIDAK DITEMUKAN DI WEBSITE | Backlog
B-04 | Service Detail - Proyek | Explain detailed scope | Apakah halaman Service Detail - Proyek membantu saya mengambil next step yang tepat? | TIDAK DITEMUKAN DI WEBSITE | Backlog
B-05 | FAQ | Resolve reviewed common questions | Apakah halaman FAQ membantu saya mengambil next step yang tepat? | TIDAK DITEMUKAN DI WEBSITE | Backlog
B-06 | Privacy Policy | Explain data processing | Apakah halaman Privacy Policy membantu saya mengambil next step yang tepat? | TIDAK DITEMUKAN DI WEBSITE | Launch blocker
B-07 | Terms & Disclaimer | Explain usage boundaries | Apakah halaman Terms & Disclaimer membantu saya mengambil next step yang tepat? | TIDAK DITEMUKAN DI WEBSITE | Launch blocker

## Content Dependencies
Content Dependencies - Aligned
Dependencies are separated between prototype tolerance and launch gate.
Page | Dependency | Status | Prototype Rule | Required | Priority
Home | Approved public contact, final service catalog, real proof | PARTIAL | Prototype may remain staging | Before launch | P1
Profile | Registration number, address detail, public contact | PARTIAL | Operator/year/city confirmed | Before launch | P1
Profile Detail | Real team approval, photos, credentials | MISSING | Dummy noindex only | Before launch | P1
Services | Approved scope, deliverables, exclusions | PARTIAL | Four categories confirmed | Before launch | P1
Our Experiences | Real cases, consent, outcomes | MISSING | Dummy prototype only | Before launch | P1
Blog/Articles | Legal/editorial review and review date | MISSING | Preview-only | Before launch | P1
Contact | Public GP contact and modal Thank You | PARTIAL | Resend confirmed | Before launch | P1
Privacy/Terms | Approved legal copy | MISSING | No invented copy | Before launch | P1
Technical | Purchased domain and verified schema | MISSING | Target domain approved | Before launch | P1

## Source Notes
Source Notes
Source hierarchy and traceability for the aligned website architecture.
Source | Priority | Function | Location
Website/codebase aktual | Primary | Implemented route, page structure, navigation, CTA, user flow, feature, and technical behavior. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\website
Dokumen Fase 2 terbaru | Secondary | Architecture and decisions; unimplemented elements are retained as backlog. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\plan\FASE 2
Dokumen Fase 1 | Tertiary | Discovery, business facts, brand foundation, user needs, and project context. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\plan\FASE 1
Brand Guidelines dan audit pendukung | Supporting | Reference only; cannot create claims or expand approved scope. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\brand
Keputusan pengguna 5 Agustus 2026 | Approval | Eleven explicit decisions controlling current/backlog, legal identity, prototype content, domain, inquiry, and governance. | Current Codex task