## Dashboard
Missing Information Dashboard - Aligned
Confirmed facts, remaining gaps, prototype tolerance, and launch blockers.
Metric | Value | Note
Total gap/decision items | 39 | Original items retained plus website-specific additions.
Unavailable | 24 | Requires content, legal, or operational input.
Waiting verification | 2 | Includes registration/domain.
Launch restricted | 5 | Must be replaced, reviewed, or removed.
Approved decisions | 11 | Eleven decisions dated 5 August 2026.
Alignment control | Prototype tolerance does not waive launch gates. No privacy/terms copy or legal registration number is invented.

## Missing Information
Daftar Informasi yang Belum Tersedia - Aligned
Original gap IDs are retained; user-confirmed items are updated and new website gaps use I-085 onward.
ID | Informasi | Status | Halaman | Owner | Release Gate | Keputusan
I-002 | Operator legal PT Karya Usaha Sukses; berdiri 2015; Kota Tangerang | TERSEDIA SEBAGIAN | Profile/legal | Project owner | Registration still required | DIPERBARUI
I-017 | Alamat jalan lengkap | BELUM TERSEDIA | Contact/footer | Company | Before launch | MENUNGGU VERIFIKASI
I-018 | Kontak publik final Galdino & Partner | BELUM TERSEDIA | Contact/header/footer | Company | Before launch | PLACEHOLDER INTERNAL
I-019 | Galdino & Partner by Kultivate | TERSEDIA | Profile/footer | Project owner | Approved | DIPERBARUI
I-021 | Domain galdinopartner.co.id | MENUNGGU VERIFIKASI | Technical | Project owner | Purchase before launch | MENUNGGU VERIFIKASI
I-025 | Jam operasional dan SLA respons publik | PERLU KONFIRMASI | Kontak, FAQ
I-044 | Deliverable per layanan | BELUM TERSEDIA | Detail layanan
I-045 | Pengecualian per layanan | BELUM TERSEDIA | Detail layanan, Terms
I-047 | Estimasi waktu dan faktor ketergantungan | PERLU KONFIRMASI | Detail layanan, FAQ
I-051 | SOP komunikasi progres dan contoh status | BELUM TERSEDIA | Profil, service details
I-053 | Checklist dokumen awal per layanan | BELUM TERSEDIA | Detail layanan, FAQ
I-055 | Tahun berdiri operator 2015 | TERSEDIA | Profile | Project owner | Approved | DIPERBARUI
I-056 | Statistics 280/120/10 | TIDAK BOLEH TAYANG | Home/Projects | Company | Evidence or remove | TIDAK BOLEH TAYANG
I-057 | Team size 9 / named team | TIDAK BOLEH TAYANG | Profile | Company | Replace dummy before launch | DATA DUMMY
I-059 | Real team credentials and photography | BELUM TERSEDIA | Profile | Company | Before launch | PLACEHOLDER INTERNAL
I-060 | Registrasi dan dokumen legal perusahaan | BELUM TERSEDIA | Profil, Terms
I-061 | Daftar proyek/case study yang boleh dipublikasikan | BELUM TERSEDIA | Pengalaman
I-062 | Sektor yang pernah dilayani | PERLU KONFIRMASI | Pengalaman, service details
I-063 | Testimoni | BELUM TERSEDIA | Pengalaman
I-064 | Logo/nama klien | BELUM TERSEDIA | Pengalaman
I-065 | Sertifikat, penghargaan, izin profesi | BELUM TERSEDIA | Profil, Pengalaman
I-066 | Checklist, SOP review, sample progress report | BELUM TERSEDIA | Profil, Pengalaman
I-067 | Hasil proyek dan waktu penanganan terukur | PERLU KONFIRMASI | Pengalaman
I-071 | Consent dan penjelasan penggunaan data | BELUM TERSEDIA | Kontak, Privacy
I-072 | WhatsApp publik | PERLU KONFIRMASI | Navbar/contact
I-073 | Email penerima inquiry CONTACT_TO_EMAIL | PERLU KONFIRMASI | Kontak
I-074 | Respons normal maksimal satu hari kerja | PERLU KONFIRMASI | Contact, FAQ
I-078 | Author/reviewer, tanggal review, sumber hukum artikel | BELUM TERSEDIA | Article detail
I-081 | Kebijakan Privasi | BELUM TERSEDIA | Privacy
I-082 | Ketentuan Penggunaan dan batas tanggung jawab | BELUM TERSEDIA | Terms & Disclaimer
I-085 | Nomor registrasi PT Karya Usaha Sukses | MENUNGGU VERIFIKASI | Profile/legal | Company | Before launch | MENUNGGU VERIFIKASI
I-086 | Approved modal/pop-up Thank You | BELUM DITERAPKAN | Contact | Website team | Before target completion | DIPERBARUI
I-087 | Legal/editorial review for six preview articles | BELUM TERSEDIA | Blog/Article | Legal reviewer | Exclude from launch | TIDAK BOLEH TAYANG
I-088 | Approved four-category service detail scope | BELUM TERSEDIA | Services | Company/legal | Before public scope claim | MENUNGGU VERIFIKASI
I-089 | Replacement/removal plan for 15 prototype services | BELUM TERSEDIA | Home | Website/content | Before launch | PLACEHOLDER INTERNAL
I-090 | Replacement/removal plan for dummy team and projects | BELUM TERSEDIA | Profile/Projects | Website/content | Before launch | DATA DUMMY
I-091 | Privacy Policy and Terms | BELUM TERSEDIA | Contact/Footer | Legal | Before launch | TIDAK DITEMUKAN DI WEBSITE
I-092 | Production robots/indexing policy | BELUM TERSEDIA | Technical | Website/SEO | Before public deployment | DIPERBARUI
I-093 | Verified Organization structured data | BELUM TERSEDIA | Technical | Website/SEO | Before launch | TIDAK BOLEH TAYANG

## Critical Gaps
Critical Information Gaps
Items affecting public identity, trust, form governance, SEO, and production readiness.
ID | Informasi | Status | Impact/Release Gate
I-017 | Alamat jalan lengkap | BELUM TERSEDIA | Contact/footer - Before launch
I-018 | Kontak publik final Galdino & Partner | BELUM TERSEDIA | Contact/header/footer - Before launch
I-021 | Domain galdinopartner.co.id | MENUNGGU VERIFIKASI | Technical - Purchase before launch
I-056 | Statistics 280/120/10 | TIDAK BOLEH TAYANG | Home/Projects - Evidence or remove
I-059 | Real team credentials and photography | BELUM TERSEDIA | Profile - Before launch
I-085 | Nomor registrasi PT Karya Usaha Sukses | MENUNGGU VERIFIKASI | Profile/legal - Before launch
I-087 | Legal/editorial review for six preview articles | BELUM TERSEDIA | Blog/Article - Exclude from launch
I-089 | Replacement/removal plan for 15 prototype services | BELUM TERSEDIA | Home - Before launch
I-090 | Replacement/removal plan for dummy team and projects | BELUM TERSEDIA | Profile/Projects - Before launch
I-091 | Privacy Policy and Terms | BELUM TERSEDIA | Contact/Footer - Before launch
I-093 | Verified Organization structured data | BELUM TERSEDIA | Technical - Before launch

## Assumptions
Approved Decision Register
Former assumptions replaced by explicit user decisions where available.
ID | Decision | Basis | Source | Impact if Changed
D-01 | Website actual is CURRENT; unimplemented Fase 2 pages remain backlog. | Approved user decision | User 2026-08-05 | If changed, all architecture/routing workbooks require revision.
D-02 | Project/Kultivate phone and email are not final public GP contacts. | Approved user decision | User 2026-08-05 | Publishing them as GP contact would be misleading.
D-03 | PT Karya Usaha Sukses is the legal operator; established 2015; Tangerang. | Approved user fact | User 2026-08-05 | Registration number still required.
D-04 | Three named team profiles are high-fidelity dummy content. | Approved user decision | User 2026-08-05 | Must remain noindex and be replaced/removed before launch.
D-05 | Fifteen service items are prototype content under four approved categories. | Approved user decision | User 2026-08-05 | Cannot be treated as final service scope.
D-06 | Six articles are preview-only and excluded from launch. | Approved user decision | User 2026-08-05 | Need review or exclusion.
D-07 | galdinopartner.co.id is the target domain but is not purchased. | Approved user decision | User 2026-08-05 | Current canonical remains placeholder.
D-08 | Thank You is a modal/pop-up, not a separate page. | Approved user decision | User 2026-08-05 | Contact UX implementation remains pending.
D-09 | Privacy/Terms remain unavailable; no new policy text is invented. | Approved user decision | User 2026-08-05 | Launch blocker remains visible.
D-10 | Galdino & Partner by Kultivate may be published. | Approved user decision | User 2026-08-05 | Must not obscure PT Karya Usaha Sukses as operator.
D-11 | Resend is the only initial inquiry integration. | Approved user decision | User 2026-08-05 | Google Sheets/CRM moved to backlog.

## Conflict Resolution
Konflik dan Resolusi - Aligned
Resolutions follow the approved source hierarchy and preserve backlog decisions.
Topic | Conflict | Decision | Priority Source
Source priority | Old blueprint prioritized Discovery over implementation | Website > latest F2 > F1 > supporting | User brief 2026-08-05
Legal identity | Website placeholder; F1/F2 pending | PT Karya Usaha Sukses operator; 2015; Tangerang | User decision
Brand relationship | Kultivate relationship pending | Galdino & Partner by Kultivate approved | User decision
Public contact | Website displays project phone/email | Classify as internal placeholder; public GP contact missing | User decision
Routes | F2 localized slugs | Use implemented English segments in both locales | Website
Page architecture | F2 15 page types | Eight current types + seven backlog groups | Website + user
Thank You | Separate page planned | Merged into modal target | User decision
Services | Four categories plus planned detail pages | Four categories retained; 15 items prototype; details backlog | Website + user
Team | Team content pending | Current names/roles are dummy high-fidelity | User decision
Articles | Article governance required | Current six are preview-only and excluded from launch | User decision
Inquiry integration | Discovery mentioned Google Sheets | Resend only for initial version | User decision
Color | Blueprint #F7F7F5 vs brand/code #F4F3F1 | Use #F4F3F1 | Website + Brand Guidelines
Policies | F2 planned Privacy/Terms | Keep as backlog/launch blockers; do not invent | Website + user

## Source Notes
Source Notes
Source hierarchy and traceability for the aligned missing-information and conflict register.
Source | Priority | Function | Location
Website/codebase aktual | Primary | Implemented route, page structure, navigation, CTA, user flow, feature, and technical behavior. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\website
Dokumen Fase 2 terbaru | Secondary | Architecture and decisions; unimplemented elements are retained as backlog. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\plan\FASE 2
Dokumen Fase 1 | Tertiary | Discovery, business facts, brand foundation, user needs, and project context. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\plan\FASE 1
Brand Guidelines dan audit pendukung | Supporting | Reference only; cannot create claims or expand approved scope. | C:\Users\Joshua\OneDrive\Documents\Law\outputs\galdino_partner\brand
Keputusan pengguna 5 Agustus 2026 | Approval | Eleven explicit decisions controlling current/backlog, legal identity, prototype content, domain, inquiry, and governance. | Current Codex task